**MSc Research Project Timeline**

1. Week 1-4, 27 May-June 14 :

**Week 1-3:**

* Review project objectives, literature, and methodologies
* Familiarize yourself with key softwares and tools.

**End of week 3:**

* You should be familiar with the literature
* You should have defined the research questions and hypotheses

🡪 you should be able to write the introduction of the thesis

* I would like you to write down a short research plan including methodology and analysis techniques.
* Feebdack

1. Week 5-8, June 17-July 12:

**Poster presentation:**

* Week 5-6: start drafting the poster
* 24 June: draft of the poster needs to be ready for feedback
* 3 July: Poster presentation

**Week 5-7:**

* Start analyzing data using appropriate statistical or qualitative analysis methods.
* Discuss preliminary findings with supervisor and refine analysis techniques as necessary.

**End of week 8:**

* You should have started to tackle your research question and have the first results.
* Feedback

1. Week 9-12, July 15-Aug 9:

**Week 9-11:**

* Interpret analyzed data and draw preliminary conclusions.
* Discuss findings with supervisor and identify any further analysis needed.

**End of week 12:**

* You should have obtained most of your results.
* You should have drafted the introduction and methodology chapters of your thesis.
* Feedback

1. Week 13: Aug 12-Aug 16:

* Finish drafting the results and discussion sections of your thesis.
* August 12: Final draft of the thesis to be handed to supervisors for feedback.

1. Week 14-15: Aug 19-Aug 30

* Address supervisor’s feedback on the thesis
* Clean and prepare code for submission as an R package
* August 30: Thesis and code submission

1. Week 16-17: Sep 2-Sep 12

* Prepare final presentation to peers or faculty members.
* September 6: Final draft of the presentation to be handed to supervisors for feedback
* September 10-13: Oral presentation
* Feedback